## Sheet1
Recruitment and Staffing Timeline
| Remote Training | In-Person Training
Open new hire recruitment posting | 6-12 weeks prior to staff list due date | 6-12 weeks prior to staff list due date
Begin screening interviews | 5-7 days after posting and on-going if needed | 5-7 days after posting and on-going if needed
Begin MBI interviews | 3-5 days after posting opens and ongoing | 3-5 days after posting opens and ongoing
Last day to make offers (start onboarding) | 3 weeks prior to staff list due date | 3 weeks prior to staff list due date
Staff list due (FRED entry deadline) | 2 weeks prior to laptop ship date | 3 weeks prior to travel date 2 weeks prior to orientation (SSL)
Welcome letter date | 1 week prior to laptop ship date | 2 weeks prior to Day 1 of training (GIT or SS) for local training/SSL no GIT 2 weeks prior to Orientaion for SSL new hires
3 weeks prior to travel date
Hire date | Welcome letter date | Welcome letter date
Laptop ship date | 5 business days prior to tech training 5 day prior to orientation (SSL) | Laptop handed out at registration
Laptop arrival date | laptop arrival 2 business days after laptop ship date
Day 1 of GIT Home Study | Welcome letter date | Welcome letter date
Tech training | 2 business days prior to day 1 of training (GIT or SS) | N/A